## Subdivisions
Subdivision and Land Development Status Report
Final Plans Approved with Conditions
Subdivisions (Revised 02/13/26)
Plan ID | Plan Name | Conditions | Approval Date | Condition Met | Date of Compliance
PRD-03-2023 | Stonegate | Conditions Accepted by Applicant on 11/21/23 | 2023-11-15
|  | 1. Outstanding Engineering comments from KU letter dated 10/03/23 |  | NO
S-03-2025 | Tuscan Hills VIII & IX | Conditions Accepted by Applicant on 06/25/25 | 2025-06-18
|  | 1. Approval of NPDES/Storm. Mgmt/Erosion Control Plans by WCD |  | NO
|  | 2. Applicant must receive sewage planning approval from NHTMA/PADEP |  | NO
|  | 3. Applicant shall enter into a Developers Agreement with TWP and |  | NO
provide bonding for public improvements
|  | 4. Applicant must acquire PADOT HOP for access on Hahntown Wendel Rd |  | NO
|  | 5. Outstanding Engineering comments from KU letter dated 06/03/25 |  | NO
S-22-2025 | St. Nikolai Drive | Conditions Accepted by Applicant on 12/01/25 | 2025-11-19
|  | 1. Applicant must receive sewage planning approval from NHTMA/PADEP |  | NO

## Site Plans
Subdivision and Land Development Status Report
Final Plans Approved with Conditions
Site Plans (Revised 02/13/26)
Plan ID | Plan Name | Conditions | Approval Date | Condition Met | Date of Compliance
SP-22-2022 | Oak Hill Dental | Conditions Accepted by Applicant on 11/22/22 | 2022-11-16
|  | 1. Approval of Stormwater Management/Erosion Control Plans by WCD |  | YES | 2022-12-21
|  | 2. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 3. Owner agrees to exterior building elevations depicted on Sheet SK3 prepared by Ulery Architecture LLC dated 09/09/22. |  | NO
|  | 4. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 5. Outstanding Engineering comments from KU letter dated 10/20/22 |  | NO
SP-23-2022 | GetGo Car Wash | Conditions Accepted by Applicant on 11/18/22 | 2022-11-16
|  | 1. Approval of Stormwater Management/Erosion Control Plans by WCD |  | YES | 2023-02-21
|  | 2. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 3. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 4. Outstanding Engineering comments from KU letter dated 10/20/22 |  | NO
SP-05-2023 | Bear Peak Power | Conditions Accepted by Applicant on | 2023-06-21
|  | 1. Outstanding Engineering comments from KU letter dated 05/23/23 |  | NO
SP-02-2016 | HMP Annex Building | Conditions Accepted by Applicant on | 2023-08-16
|  | 1. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 2. Annex building overall height shall not be governed by the Shopping Center Ordinance |  | NO
|  | 3. Annex architectural elevations on floors 2, 3, and 4 shall not be governed by the Shopping Center Ordinance but the first floor will be |  | NO
|  | 4. Parking and Landscaping will be governed by the Shopping Center Ord. |  | NO
|  | 5. Applicant must supply reciprocal parking easements for whole site |  | NO
|  | 6. Owner agrees to exterior building elevations depicted on drawings prepared by Design 3 Architecture |  | NO
|  | 7. All uses for annex building shall follow C-1 standards |  | NO
SP-06-2023 | Cleaveland Price Parking | Conditions Accepted by Applicant on 08/28/23 | 2023-08-16
|  | 1. Applicant must require PADOT HOP for driveway access |  | NO
|  | 2. Approval of NPDES/Storm. Mgmt/Erosion Control Plans by WCD |  | YES | 2023-12-06
|  | 3. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 4. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 5. Outstanding Engineering comments from KU letter updated 08/01/23 |  | NO
SP-08-2023 | Hamilton Automotive | Conditions Accepted by Applicant on 10/24/23 | 2023-10-18
|  | 1. Approval of Stormwater Management/Erosion Control Plans by WCD |  | NO
|  | 2. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 3. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 4. Outstanding Engineering comments from KU letter dated 09/19/23 |  | NO
SP-10-2023 | Leader Properties Plaza | Conditions Accepted by Applicant on 03/26/24 | 2024-03-20
|  | 1. Owner waives all development rights until final approval is achieved |  | NO
SP-03-2025 | Sheetz Carpenter Lane | Conditions Accepted by Applicant on 06/25/25 | 2025-06-18
|  | 1. Approval of NPDES/Storm. Mgmt/Erosion Control Plans by WCD |  | NO
|  | 2. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 3. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 4. Applicant to provide documentation of existing access easement |  | NO
|  | 5. Applicant will provide architectural elevations per company standards |  | YES
|  | 6. Outstanding Engineering comments from KU letter dated 05/23/25 |  | YES | 2025-12-22
SP-06-2025 | Bear Peak N. Huntingdon | Conditions Accepted by Applicant on 07/31/25 | 2025-07-16
|  | 1. Owner waives all development rights until final approval is achieved |  | NO
|  | 2. Outstanding Engineering comments from KU letter dated 06/25/25 |  | NO
SP-13-2025 | Cleaveland Price Expansion | Conditions Accepted by Applicant on 10/01/25 | 2025-09-17
|  | 1. Approval of NPDES/Storm. Mgmt/Erosion Control Plans by WCD |  | NO
|  | 2. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 3. Applicant must receive NHTMA approval for sanitary sewer design |  | NO
|  | 4. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 5. Outstanding Engineering comments from KU letter dated 08/19/25 |  | NO
SP-21-2025 | Guardian Storage | Conditions Accepted by Applicant on 11/26/25 | 2025-11-19
|  | 1. Approval of NPDES/Storm. Mgmt/Erosion Control Plans by WCD |  | NO
|  | 2. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 3. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 4. Outstanding Engineering comments from KU letter dated 10/14/25 |  | NO
SP-22-2025 | Somerset Trust Plan | Conditions Accepted by Applicant on 12/02/25 | 2025-11-19
|  | 1. Approval of NPDES/Storm. Mgmt/Erosion Control Plans by WCD |  | NO
|  | 2. Applicant shall enter into a Stormwater O&M agreement with TWP |  | NO
|  | 3. Applicant shall enter into a Commercial Developers Agreement with TWP |  | NO
|  | 4. Applicant will provide elevations per company standards |  | NO
|  | 5. Applicant must acquire PennDOT HOP for driveway access |  | NO
|  | 4. Outstanding Engineering comments from KU letter dated 10/21/25 |  | NO